___________________________________________________________________________

2009/HRDWG31/064

Item: EDNET

- Project Proposal (Operational Account): Capacity-Building Seminar on the Development of National Qualification Frameworks

Purpose: Consideration

Submitted by: Philippines

|  | - 31st Human Resources Development Working Group Meeting - Chicago, United States - 22-25 June 2009 |
| --- | --- |

#### APEC PROJECT PROPOSAL

#### Facesheet

| Name of Committee/Working Group: HRD Working Group |  |  |  |
| --- | --- | --- | --- |
| Title of Project: Capacity-Building Seminar on the Development of National Qualification Framework(s) |  |  |  |
| Proposing APEC Economy: 1) Philippines |  |  |  |
| Co-sponsoring APEC Economies: 2) ___________ ; 3) ____________ |  |  |  |
| Project number: |  | Date received by Secretariat: |  |
| [ ] Project seeking APEC funding [ ] Progress Report [ ] Evaluation Report |  |  |  |
| [ ] Operational Account [ ] TILF Special Account [ ] APEC Support Fund [ ] QAF attached [ ] QAF not applicable [ ] QAF attached |  |  |  |
| Financial Information | Total cost of proposal (US$): US$ 98,518 |  | Amount being sought from APEC funding US$ 76,818 |
| Type of Project: [ ] seminar/symposium [ ] short-term training course [ ] survey or analysis and research [ ] database/website [ ] other |  |  |  |
| Project start date: January 2010 |  | Project end date: December 2010 |  |
| Brief Description of Project -- its purpose and the principal activities (including when and where): Current developments in higher education present several challenges to higher education systems, particularly, the Philippines with a developing higher education system. One concern that higher education systems need to address is the increasing mobility of profession, which provides the need for a common professional qualification as basis for a regional and global standards for recognition, credit and transfer system. Efforts have been initiated to promote quality, increase mutual understanding, enhance cooperation and collaboration in higher education between and among APEC member economies and other countries. In addition, it is imperative to build on and develop the capability of the manpower for a sustained progress of any member economy. The Philippines proposes to hold a seminar that will serve as a forum for sharing insights, policies, notes of experience on “best” practices and standards on the development of national qualifications framework(s) for recognition, credit and transfer system. The Seminar shall facilitate and provide the platform for a dialogue among educators and policy-makers in developing national qualifications framework(s) anchored on quality assurance systems. Indeed, APEC and some regional agencies such as UNESCO and ASEAN have done some efforts in developing such framework which may be considered for integration The Seminar is being proposed to be held in Manila, Philippines in September 2010. This proposal seeks funding for attendance (travel, per diems and honoraria in the case of speakers) of 26 participants: four (4) speakers and 22 representatives from APEC travel-eligible economies. |  |  |  |
| Project Overseer: Name, Title and Organization (F) Julito D. Vitriolo Executive Director Commission on Higher Education (Philippines) |  |  |  |
| Postal address: Higher Education Development Center C.P. Garcia Ave., Diliman, Quezon City Philippines |  | Tel: +63 (2) 441 1216 Fax: +63 (2) 441 1216 E-mail: jdvitriolo@yahoo.com |  |
| Signature of Project Overseer: Date: |  |  |  |
| Signature of Committee Chair/WG Lead Shepherd: Date: |  |  |  |

Details of the Project Proposal

A.	Project Design

Project Objectives

- Describe briefly how this project directly responds to the priorities set by APEC Leaders and Ministers and/or the vision of the host economy. Please make reference to the relevant parts of APEC documents.

“Developing 21st Century Workforce is to strengthen the human resource development and promote sustainable economic growth.”   The HRD working group's mission in developing 21st Century recognizes the necessity of globalizing opportunities for a sustained human economic growth facilitated in by a globally competitive workforce.

This mission was reinforced during the 30th HRDWG meeting in Bohol, Philippines in April 2008 and during the 4th APEC Education Ministerial Meeting (AEMM) in Peru, Lima in June 2008, wherein APEC economies are being encouraged tin pursuing activities ensuring quality education and competencies for all to improve human resource capabilities throughout the APEC region.

This proposal shall facilitate the achievement of the following goals:

- establishment of a multi-sectoral cooperation and collaboration in the development of qualifications framework(s);

- sharing of policies, standards and considerations,  and promotion of “best” practices in the development of national qualifications framework(s) for recognition, credit and transfer system.

- development of a system of recognition, credit and transfer system;

- provision of an accurate, up-to-date, and accessible information on higher education systems and recognition of qualifications;

- establishment of a higher education network between and among the APEC economies in sharing information and in implementing appropriate regulations or a common framework for national qualifications.

- Describe the key objectives of the project

Key objectives of this seminar are the following:

Identify policy, standards, criteria and regulatory concerns  in the comparability of higher education systems and mutual recognition to facilitate development of qualifications framework(s) including the setting up and implementation of quality assurance systems, recognition of institutions and programs as bases for the  credit and transfer system, and the adoption of good practices;

Promote public-private partnership among government agencies, educational groups, and professional organizations and network among economies;

Inform policy makers and educators of the directions, relevant policies, rules and regulations and other agreements that affect the implementation of a qualification framework and recognition system.

- Assessment. With reference to each objective in paragraph 2), provide the current status and expected end-of-project target, so that the success of the project can be measured over the short and medium term.

Objective 1: Identify policies, standards, criteria and regulatory concerns—in the comparability of higher education systems to facilitate development of qualifications framework(s) including the setting up and implementation of  quality assurance systems, recognition of institutions and programs as bases for the  credit and transfer system, and the adoption of good practices. APEC economies have varying higher education systems. The nature of globalizing profession necessitates recognition of professionals/ human resource acceptable internationally. This seminar shall provide a forum for taking stock of current policies and regulatory perspectives and practices on higher education systems throughout the region. Economies shall share views and insights on their systems, particularly, quality assurance systems, criteria, procedures and “good” practices in implementing qualifications framework and recognition systems  as contained in their presentation and discussion papers. The seminar shall serve as a venue to learn from the experience of both developed and developing economies and from a varied set of participants (business, regulatory officials, educators, administrators of higher education institutions, other stakeholders).

Participants from APEC member economies shall explore the applicability of practices and determine strategies to effectively develop and implement regulatory concerns and reforms. Participants shall also discuss opportunities, corresponding risks, and barriers to regulatory reforms, taking into account the perspective of developed and developing economies.

Objective 2: Promote public-private partnership in establishing and implementing policies, standards, criteria and regulations. Presentations shall focus on identifying potential areas of cooperation between government agencies and educational groups and among economies in the development and implementation of  qualifications framework(s), particularly, in the recognition, credit and transfer system.

Objective 3: Inform policy makers and educators of the directions, relevant policies, rules and regulations, and other agreements that affect the development and implementation of a qualifications framework.  APEC shall consider the said information as bases for in the development of standard policies and procedures in the establishment and implementation of qualifications framework(s). In addition, these data shall be made available and accessible to stakeholders.

Current status: The Commission on Higher Education (CHED) as lead agency aims to publish the Philippine national qualifications framework which will serve as basis for the competencies required and system of recognition of professions, credit and transfer.

In addition, the  framework shall consider the Philippines’ directions on higher education and other economies’ directions: e.g., quality assurance systems, efforts initiated by any regional organizations such as  UNESCO and ASEAN; commitments entered into by the Philippine Government such as the General Agreements on Trade and Services (GATS) and ASEAN Framework Agreement on Services; and adoption of best practices on the development, delivery, implementation, management and monitoring of higher education systems,   particularly, the experiences of UK, Canada, Australia, New Zealand and other economies with defined qualifications framework and established recognition, credit and transfer system.

- Explain who the intended beneficiaries of this project are.

Stakeholders from APEC economies: regulatory agencies, professionals, higher education institutions, faculty and students.

- Describe precisely the expected project outputs. Describe how these outputs will benefit the targeted beneficiaries.

This project is designed to provide a forum to discuss policies, standards, criteria and practices in the development national qualifications framework(s) to ensure acceptability of professions in between and among APEC economies, the establishment of quality and  legitimate  arrangements within APEC economies. The Seminar shall hence benefit stakeholders by promoting appropriate qualifications framework, effective cooperation and collaborative arrangements and  practices in implementing recognition, credit and transfer system.

Specific outputs from this project shall be (a) convening a seminar to discuss policies, standards, criteria and practices in the development and implementation of qualifications framework(s); and 2) developing guidelines to assist member economies in developing and implementing systems comparable to any higher education systems within the region and among APEC economies.

- For applications under the TILF Special Account: Describe briefly how this project will contribute to the APEC Trade and Investment Liberalization and Facilitation (e.g. relevance to specific parts of the Osaka Action Agenda).

Not applicable

Linkages

- Which other APEC fora have been consulted about this project and what were the results?

The APEC HRD Education Network shall be requested to review and comment on this proposal.

- Active Participation Describe how the intended beneficiaries among APEC stakeholders –APEC fora, governments, private sector and civil society, men/women- will participate in the planning, implementation and evaluation of the project.

Stakeholders from both the public and private (officials, educators, professionals, etc) sectors shall participate actively in this seminar. Hence, presentations on “good”/successful practices and challenges shall reflect a mix of developing and developed perspectives from both the public and private sectors. These presentations shall serve as basis for developing a national qualifications framework(s)  appropriate for the member economies.

- Project influence Describe how this project might contribute to any current or completed projects or activities in APEC or elsewhere. Why is APEC the most appropriate institution to fund the project?

This project responds directly to guidance provided by Ministers and Leaders to develop an APEC work program on multi-sector cooperation and development, and seeks to build on outcomes from the recent APEC projects on GOS. The Seminar addresses cross border concerns including policies on and economic activity and thus complements APEC’s work to promote sustainable growth and trade through trade and investment liberalization and facilitation, as well as its structural reform agenda.

Outputs of this project shall serve as an input to the APEC EDNET theme, which is Achieving 21st Century Competencies and skills.

Methodology

- Describe the project’s methodology. Break down the project implementation into discrete functional steps over time with the associated outputs clearly specified. Identify the principal risks involved in each step if any, and explain how they will be managed.

A three-day Seminar shall be held in Manila in September 2010, with experts and stakeholders from APEC member-economies participating in presentations, open discussions, and a closing round-table and evaluation of the activity.

The risks involved in the workshop/publication phase of the project include:

- late submissions of presentation materials and other relevant documents from 	participating economies may delay the collation of materials for the Seminar;

- flight delays or cancellations may prevent researchers and officials from attending 	the workshop.

CHED shall designate a project coordinator to minimize these risks. The project coordinator shall be responsible for coordinating the participation of representatives from APEC economies, submission of economy papers before the Seminar, overseeing the administrative arrangements for the Seminar proper, including the documentation of the results and their dissemination in APEC.

- Which APEC member economies will participate in each component of this project and what contribution are they expected to make?

Representatives from government agencies, educational groups, and professional organizations from all APEC member economies shall be invited. The lead agency for implementing this project shall be the Commission on Higher Education, which needs to develop and publish a national qualifications framework for higher education, in collaboration with the Department of Education (DEPEd) and Technical Education, Skills and Development Authority (TESDA). APEC economies shall help identify and invite guest speakers and participants.

Dissemination of Project Output

- Please include a plan for the publication and dissemination of the results of the project, including:

              - the nature of the target audience;

              - the form and content;

              - format (e.g. hard copies, floppy discs, internet uploading);

              - number of copies for the publication;

              - a publicity plan for:

      - briefing the general or specialist media about key components of the project;

      - the promotion of sales or other dissemination of the final product; and

f. a budget for publication and dissemination, to form part of the itemized budget.

The Seminar’s outcomes shall be posted on the GOS AIMP (APEC Information Management Portal) to facilitate access by interested stakeholders. In addition, the Commission shall disseminate the results/outcomes to its stakeholders—including higher education institutions—via print and online media.

Project benefits shall be made sustainable by ensuring that the Seminar outputs can serve as substantive inputs to the individual efforts of APEC economies in crafting their qualifications framework .

Gender Concerns

- Many projects have the potential to affect men and women differently because of their different roles and positions in many societies. What steps does this project take to ensure that it benefits both groups and in particular does not disadvantage women? (Common responses include: using gender analysis to design project methodologies and inputs (e.g. surveys); including women in the planning, management, allocation of resources and implementation of a project; taking steps to ensure equitable participation by men and women; making special efforts to disseminate project results to women; and using sex-disaggregated data for project assessment.)

Indeed, there is no doubt that the Project shall contribute to the empowerment of women in a developing economy like the Philippines. Currently, the higher education has an enrollment trend of about 400,000 both men and women with about one (1) percent increase each year, particularly,  given the popularity of education as a profession among Filipino women and the relative predominance of women in the work force of educational institutions and regulatory agencies.

This project shall benefit women both directly and indirectly, in particular through its potential benefits to professionals and the directions for sustaining human resources, particularly for lifelong and continuous learners in the APEC region. It shall help build institutional and individual capacities, with no gender distinction.

Women have already been taking a lead role in the early stages of planning for the project at the Commission on Higher Education: from support staff to the resource persons from other government and non-government agencies and to administrators of higher education institutions and implementers being consulted by CHED. Female participants shall be encouraged to participate in the planning, management, and implementation of the project, including the participation of female experts and participants in the Seminar. The project proponent shall ensure equitable participation by men and women and disseminate project results to women. Use of sex-disaggregated data for project assessment shall also be explored.

- Show how the objectives of the project provide benefits for women. APEC Ministers have indicated (Framework for the Integration of Women in APEC) that benefits might include: increasing the involvement of women in the economy and economic institutions; integrating women into the global economy; strengthening small and medium sized enterprises; and reducing gender inequalities, including through education and training.

Improving women’s access to quality education helps reduce gender inequalities. The increasing number of women administrators also indicates reduced gender issues in managing education or any services. Therefore, this project shall benefit women by upgrading the capacity of APEC economies in developing and implementing national qualifications framework at the APEC region

Budget

- Please attach an itemized budget for the project in the format at Annex A. Where appropriate, provide details of the project’s budget that are allocated to activities that address the specific needs of women. The budget should illustrate the assumptions adopted (e.g. unit costs) for the computations. Remember to include all self-funding and to consult the list of eligible expenses in the Guidebook to APEC Projects. Advice on budget formulation, including acceptable unit costs, can be sought from the APEC Secretariat.

Please see Annex A.

- A timetable for the drawdown of APEC funding requested for the project, including details of any advance payment or installment payment requested and justifications for such requests.

Drawdown will be done in accordance with APEC procedures and on advice from the APEC Secretariat.

| Activity | Timeframe |
| --- | --- |
| 1. Finalization/ approval of the APEC Proposal | June to September 2009 |
| 2. Planning/ Meeting and agreements on arrangements | October to December 2009 |
| 3. Program Development/ identification of Seminar venue | January to March 2010 |
| 4. Website Development/ dissemination of invites | February 2010 |
| 5. Confirmation of invited a) resource persons b) participants | March to May 2010 |
| 6. Gathering of presentation materials | May to July 2010 |
| 7. Finalization of accommodation and other related arrangements | June to August 2010 |
| 8. Actual Seminar | September 2010 |
| 9. Preparation/ finalization/ publication of proceedings | October 2010 to December 2010 |

- Details of any request for waiver or exception from the normal APEC financial rules with justifications. (Examples are from tendering requirements; for advance payment; for government officials to receive funding; for active participants from travel-eligible economies to receive per diems)

This proposal requests that funding be available for airfares for up to two government officials from travel-eligible economies to help ensure relevant and broadly representative attendance by member economies.

This proposal requests that permission for advance payment be approved in principle should this prove necessary in arranged flights and accommodation.

No other waivers or exemptions are requested.

Annex A

APEC Project

Itemized Budget for Financial Year 2008

(Please tick )

This project is:

	a seminar, symposium or short-term training course

	a survey or analysis and research project

	neither the above but involves the provision of equipment

| Items | No. of Units |  | Unit Rate | APEC Funding (USD) | Self Financing (USD) |  |
| --- | --- | --- | --- | --- | --- | --- |
| Direct Labor |  |  |  |  |  |  |
| Speaker’s Honorarium (govt officials ineligible) | 4 speakers | $1000 |  | 4000 |  |  |
| - Translator’s Fees |  |  |  |  |  |  |
| - Short-term clerical and secretarial staff remuneration | Documentation and Secretariat 240 x 6 | $ 15/ hour |  |  |  | 14600 |
| - Consultant (including Researcher) Fees | Not applicable |  |  |  |  |  |
| - Consultant’s Secretary Cost | Not applicable |  |  |  |  |  |
| Travel (Speakers) |  |  |  |  |  |  |
| Per Diem (incl. accommodation and “additional payment”) | 4 Speakers x 4 days | $183 per person/ per day |  | 2928 |  |  |
| - Airfares | 4 Speakers | $4000 average in consideration for those speakers that might travel for more than 12 hrs. |  | 16000 |  |  |
| Travel (Active participants) (travel-eligible economies) |  |  |  |  |  |  |
| - Per Diem (incl. accommodation and “additional payment”) (active participants) | 20 participants from developing economies x 4 days | $183 per person |  | 14640 |  |  |
| - Airfare (restricted economy class) | 20 participants from developing economies | 1400 average |  | 28000 |  |  |
| Other items |  |  |  |  |  |  |
| Publication of report (including distribution) | 200 hard copies and CD ROM |  |  | 4000 |  |  |
| Equipment / Materials (describe briefly what is required and why) | IT Equipment, multi-media and overhead equipment rental and supplies for 3 days |  |  |  |  | 5100 |
| Photocopying |  |  |  |  |  |  |
| Communications (Phone/Fax/Mail/Courier) |  |  |  |  |  | 2000 |
| Hosting (pl. briefly describe, eg, conference room rental, stationery) | Rental of venue x 3 days | $2500 |  | 7250 |  |  |
| Total |  |  |  | US$76,818 |  | US$21,700 |